## Graph
Activity | Start Date | End Date | Duration
Automation Phase I | 2020-11-23 | 2020-11-27 | 5
Automation Phase II | 2020-11-30 | 2020-12-04 | 5
Automation Phase III | 2020-12-07 | 2020-12-11 | 5
Automation Phase IV | 2020-12-14 | 2020-12-18 | 5
Automation Phase V | 2020-12-21 | 2020-12-25 | 5
Automation Phase VI | 2020-12-28 | 2021-01-08 | 12
ORC-26027 Preparation | 2020-11-27 | 2020-11-27 | 1
ORC-26027 Execution | 2020-11-30 | 2020-11-30 | 1
ORC-26028 Preparation | 2020-12-02 | 2020-12-02 | 1
ORC-26028 Execution | 2020-12-15 | 2020-12-16 | 2
ORC-26029 Preparation | 2020-12-07 | 2020-12-08 | 2
ORC-26029 Execution | 2020-12-21 | 2020-12-30 | 10
ORC-26068 Preparation | 2020-11-26 | 2020-11-27 | 2
ORC-26068 Execution | 2020-01-04 | 2020-01-11 | 8
ORC-26069 Preparation | 2020-12-03 | 2020-12-03 | 1
ORC-26069 Execution | 2020-12-10 | 2020-12-11 | 2
System Testing | 2020-01-12 | 2020-01-20 | 9
Training | 2020-01-27 | 2020-01-29 | 3

## Manual_CR
Jira ID | Description | QA Delivery Date | Prepartaion |  | Execution Start date | Execution End Date | SignOff Date | Internal Start Dates | Internal End Date | Sys Test | Regression start date | End Date
ORC-26027 | Improve Assignment Search | 2020-11-28 | 2020-11-27 | 2020-11-27 | 2020-11-30 | 2020-11-30 | 2020-12-09
ORC-26028 | Merge Queries in Lead/Assignment Tab | 2020-12-14 | 2020-12-02 | 2020-12-02 | 2020-12-15 | 2020-12-16 | 2020-12-22
ORC-26029 | Application Insights | 2020-12-19 | 2020-12-07 | 2020-12-08 | 2020-12-21 | 2020-12-30 | 2020-01-11
ORC-26068 | Window 7 to Window 10 | 2020-11-28 | 2020-11-26 | 2020-11-27 | 2020-01-04 | 2020-01-11 | 2021-01-12 | 2020-12-31 | 2020-01-08
ORC-26069 | Merge Queries in People-Details tab. | 2020-12-07 | 2020-12-03 | 2020-12-03 | 2020-12-10 | 2020-12-11 | 2020-12-17 |  |  | 2020-12-10
REP-3389 | [Mail merge report not generating] FW: Orchestra event mail merge [IR147374]
System testing end date | [5 empty] | 2020-01-11
Orc 11.0 Regression |  |  |  |  | 2020-01-12 | 2020-01-20 | 2020-01-25 | 2020-01-25
Training |  |  |  |  | 2020-01-27 | 2020-01-29 | 2020-01-29
Live | [6 empty] | 2020-01-30
Formulas:
Execution Start date = [QA Delivery Date]+2
Execution End Date = [Execution Start date]+0

## UIAutomation
UIAutomation | Start date | End Date | Not-Started % | Completion % | In-Progress % | On-Hold %
Phase I | 2020-11-23 | 2020-11-27 | 0 | 100 | 0 | 0
Phase II | 2020-11-30 | 2020-12-04 | 0 | 88 | 12 | 0
Phase III | 2020-12-07 | 2020-12-11 | 50 | 25 | 25 | 0
Phase IV | 2020-12-14 | 2020-12-18 | 38 | 31 | 31 | 0
Phase V | 2020-12-21 | 2020-12-25 | 73 | 27 | 0 | 0
Phase VI | 2020-12-28 | 2021-01-08

## Manual_TestScenario
Modules | Status | Total Percentage | Completed %
People | Completed | 10 | 10
Company | Completed | 10 | 10
Lead | Completed | 20 | 10
Assignment | In-Progress | 30 | 5
Event | Not-Started | 10 | 0
Call List | Not-Started | 10 | 0
ETP Relationship | Not-Started | 10 | 0

## UIAutomation PhaseI
S.No | Test Case Criteria | Tab | Description | Steps | Owner | Status | Remarks
1 | Low | People_Tab | Click on People |  | Aarti | Automated
2 | Low | People_Tab | Create People record Quick Entry |  | Aarti | Automated
3 | Medium | People_Tab | Person Tab | ~ Mr/Ms ~ First Name ~LastName ~ Known As ~ Addr. As ~ Name in Local Language ~ Principal Nationality ~ Earl.Qual ~Email ~Phone | Aarti | Automated
4 | High | People_Tab | Work History | ~ Seq. No ~ Prm ~ Past ~ Hired ~ from ~ To ~ Ultimate Parent ~ Company ~ Position ~ Division ~ Country ~ Base Salary ~ Short-term Bonus ~ Work History Details ~Assistant ~ Compensation | Aarti | Automated
5 | Low | Company_Tab | Click on Company |  | Reema | Automated
6 | Low | Company_Tab | Create Company | Create company clicking on "Add New" | Reema | Automated
7 | High | Company_Tab | General Tab | 20 Fields | Reema | Automated
8 | Low | Lead_Tab | Search and Click on Lead |  | Reema | Automated
9 | High | Lead_Tab | Executive Search | Lead-I (20 fields) | Reema | Automated

## UIAutomation PhaseII
S.No | Test Case Criteria | Tab | Description | Steps | Owner | Status | Remarks
1 | Medium | People_Tab | Verify WorkHistory on Person Tab | ~ From ~ To ~ Position ~ Company ~ Country | Aarti | Automated
2 | Medium | People_Tab | Personal Tab | ~ Person Alert ~ Corr. Line ~ Spouse's Name ~ Martial Status ~ Children ~ Lifestage Indicaor ~ Principal Nationality ~ Birthdate ~ Other Nationality 1 ~ Language ~ Home Addr ~ Business Addr. ~ Alternative Addr. ~ Countries Exp. ~ Admin | Aarti | Automated
3 | Medium | People_Tab | Qualification Tab | ~ Seq. No. ~ Qualification Type ~ Qualificaion Name ~ Local Language Qualification Name ~ Institution ~ Graduation Year ~ Country ~ Verified On ~ Verified By | Aarti | Automated
4 | Low | People_Tab | FileNotes | File Note Type-10 | Aarti | Automated
5 | Medium | People_Tab | Search and Power Search after record is created |  | Aarti | Automated
6 | High | Lead_Tab | Executive Search | Teams (20 fields) | Aarti | Automated
7 | Medium | Company_Tab | Addresses | ~ Address Details (11 fields) ~ Contacts At this Address | Reema | Automated
8 | High | Company_Tab | Client Activities | Leads | Reema | In-Progress
9 | High | Company_Tab | Client Activities | Assignment | Reema | In-Progress
10 | High | Lead_Tab | Executive Search | Lead-II (20 fields) | Reema | Automated
11 | High | Lead_Tab | Executive Search | Fees-I(21 fields) | Reema | Automated
12 | High | Lead_Tab | Executive Search | Fees-I(20 fields) | Reema | Automated
13 | High | Lead_Tab | Executive Search | Invoice Details -I (25 fields) | Reema | Automated
14 | High | Lead_Tab | Executive Search | Invoice Details-II(20fields) | Reema | Automated
15 | Low | Assignment_Tab | Search or Click on Assigment |  | Jamal | Automated
16 | High | Assignment_Tab | Executive Search | Assignment (40 fields) | Jamal | Automated
17 | High | Assignment_Tab | Executive Search | Fees-I (21 fields) | Jamal | Automated
18 | High | Assignment_Tab | Executive Search | Fees-II (20 fields) | Jamal | Automated
19 | High | Assignment_Tab | Executive Search | Invoice Details -I (20 fields) | Jamal | Automated
20 | High | Assignment_Tab | Executive Search | Invoice Details -II (25 fields) | Jamal | Automated
21 | High | Assignment_Tab | Executive Search | Teams (20 fields) | Jamal | In-Progress
22 | High | Assignment_Tab | Executive Search | Research (Add candidate/Verify added candidate) | Jamal | Automated
23 | Low | Assignment_Tab | Executive Search | Move to Source | Jamal | Automated
24 | Medium | Assignment_Tab | Executive Search | Source (Add candidate/Verify added candidate) | Jamal | Automated
25 | Low | Assignment_Tab | Executive Search | Move to Potential Target | Jamal | Automated
26 | High | Assignment_Tab | Executive Search | PT(Add candidate/Verify added candidate) | Jamal | Automated

## UIAutomation PhaseIII
S.No | Test Case Criteria | Tab | Description | Steps | Owner | Status | Remarks
1 | High | Lead_Tab | Executive Search | Codes (23 fields) | Reema | Automated
2 | Medium | Lead_Tab | Executive Search | Verify documenets (10 clicks) | Reema | In-Progress
3 | High | Lead_Tab | Executive Search | Research (Add candidate/Verify added candidate) | Reema | Not Started
4 | Low | Lead_Tab | Executive Search | Move to Source | Reema | Not Started
5 | Medium | Lead_Tab | Executive Search | Source (Add candidate/Verify added candidate) | Reema | Not Started
6 | High | Lead_Tab | Executive Search | Linked Companies | Reema | In-Progress
7 | Low | Assignment_Tab | Executive Search | Move to Target | Aarti | Automated
8 | High | Assignment_Tab | Executive Search | Target (Add candidate/Verify added candidate) | Aarti | Automated
9 | Low | Assignment_Tab | Executive Search | Move to Interested | Aarti | Automated
10 | High | Assignment_Tab | Executive Search | Interested (Add candidate/Verify added candidate) | Aarti | In-Progress
11 | Medium | Assignment_Tab | Executive Search | Add Interview details | Aarti | In-Progress
12 | Medium | Assignment_Tab | Executive Search | Add presented Candidate | Aarti | Not Started
13 | High | Assignment_Tab | Executive Search | Add presented Details | Aarti | Not Started
14 | High | Assignment_Tab | Executive Search | Closing (30 fields) | Aarti | Not Started
15 | High | Assignment_Tab | Executive Search | Integration (15 fields) | Reema | Not Started
16 | High | Assignment_Tab | Executive Search | Progress | Reema | Not Started

## UIAutomation PhaseIV
S.No | Test Case Criteria | Tab | Description | Steps | Owner | Status | Remark
1 | High | Assignment_Tab | Executive Search | Add file note (10 fields/clicks) | Reema | Not Started
2 | Medium | People_Tab | Verify the Lead on Person Tab | Complete grid | Reema | Not Started
3 | High | People_Tab | CV | ~ CV Name ~ File Type ~ CV Language ~ Created ~ Created By ~ Updated ~ Updated By | Reema | Not Started
4 | High | People_Tab | Event | 30 fields | Reema | Not Started
5 | High | People_Tab | OCET | 5 Fields _URL Page | Reema | Not Started
6 | High | People_Tab | Documents |  | Reema | Not Started
7 | Low | CallList | Click on Call List |  | Aarti | Automated
8 | High | CallList | Search and Add People into Call List | Search and Add People into Call List | Aarti | Automated
9 | Low | CallList | Remove the candidate | Remove | Aarti | Automated
10 | Low | ETP Relationship | Click on ETP |  | Aarti | Automated
11 | High | ETP Relationship | Search and Add People into Relationship | Search and Add People into ETP | Aarti | Automated
12 | Medium | ETP Relationship | Add as PP | Add as PP | Aarti | In-Progress
13 | Medium | ETP Relationship | Add as Bronze | Add as Bronze | Aarti | In-Progress
14 | Medium | ETP Relationship | Add as Silver | Add as Silver | Aarti | In-Progress
15 | Medium | ETP Relationship | Add as Gold | Add as Gold | Aarti | In-Progress
16 | Low | ETP Relationship | Remove candidate | Remove candidate | Aarti | In-Progress

## UIAutomation PhaseV
S.No | Test Case Criteria | Tab | Description | Steps | Owner | Status | Remark
1 | Low | Event_Tab | Click on Event |  | Aarti | Automated
2 | High | Event_Tab | Add Event | 22 fields | Aarti | Automated
3 | High | Event_Tab | Add codes | 10 fields | Aarti | Not Started
4 | High | Event_Tab | Add Teams | 10 fields/clicks | Aarti | Not Started
5 | High | Event_Tab | Add invitee | 18 fields | Aarti | Not Started
6 | High | Event_Tab | Add Document |  | Aarti | Not Started
7 | Medium | Event_Tab | Add file notes |  | Aarti | Automated
8 | Medium | People_Tab | Delete People record |  | Aarti | Not Started
9 | Medium | Company_Tab | Delete Company |  | Aarti | Not Started
10 | Medium | Lead_Tab | Executive Search | Delete Lead | Aarti | Not Started
11 | Medium | Assignment_Tab | Executive Search | Delete Assignment | Aarti | Not Started

## Defects
Defect | Reopened | Status | Logged Date | Resolved Date | Closed Date

## ResourcesLeave
Resource
Reema
Aarti | 27-1 Dec | 7-8 Dec | 11-15 Dec | 22-23 Dec
Nidhi
Jamal | 2020-12-11 | 23-25Dec

## Sheet13
Not Started
Automated
In-Progress
On Hold